## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User Story Description | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | CapStore Pdf | Must | US:1 | Customer Profile Page | Profile page of customer where customer can changes there personal details and can see his orders | Customer |  | Average | Medium |  |  | Functional
2 | 2 | CapStore Pdf | Must | US-2 | Product's Images | Managing the products images | Customer |  | Complex | Medium |  |  | Technical
3 | 3 | CapStore Pdf | Must | US-3 | CapStore HomePage | Homepage of capstore where customer will interact | Customer |  | Average | High |  |  | Functional
4 | 4 | CapStore Pdf | Must | US-4 | Product Page | product page where customer can add the product to his card | Customer |  | Average | High |  |  | Functional
5 | 5 | CapStore Pdf | Must | US-5 | Return Goods | Goods returned by customer for some reason | Customer |  | Average | Medium |  |  | Functional
6 | 6 | CapStore Pdf | Must | US-6 | Generate Invoice | Invoice generated after placing the order | Customer |  | Average | Low |  |  | Functional
7 | 7 | CapStore Pdf | Must | US-7 | Sign Up & Activation | Ragistration for non existing user of Capstore | Admin |  | Average | High |  |  | Functional
8 | 8 | CapStore Pdf | Must | US-8 | Admin Page | First Page of Administratior of Capstore can view all Customer,Merchant and the complete inventory | Admin |  | Average | High |  |  | Functional
9 | 9 | CapStore Pdf | Must | US-9 | Business Analysis | Check dispatch report of particular product,Category of products or products from a particular merchant | Admin |  | Complex | High |  |  | Functional
10 | 10 | CapStore Pdf | Must | US-10 | Managing Merchant | Admin can add or remove merchant | Admin |  | Average | Medium |  |  | Functional
11 | 11 | CapStore Pdf | Must | US-11 | Checking ,Updating Status of Delivery | Admin will update the status of delivery of products.Customer can check status of delivery | Admin |  | Average | Low |  |  | Functional
12 | 12 | CapStore Pdf | Must | US-12 | Merchant Profile Page | First Page of Merchant of Capstore can view all orders placed by customers and the complete inventory of his products | Merchant
13 | 13 | CapStore Pdf | Must | US-13 | Managing inventory | Merchant can add or remove items in the inventory,Add or remove category,update inventory | Merchant
14 | 14 | CapStore Pdf | Must | US-14 | Search products and orders | Merchant can search in its own inventory and orders | Merchant
15 | 15 | CapStore Pdf | Must | US-15 | Image Upload | Merchant can upload images for his products | Merchant
16 | 16 | CapStore Pdf | Must | US-16 | Delivery Products | After successfully placing an order product will be deliverd to the customer and inventory will be updated | Merchant
17 | 17 | CapStore Pdf | Must | US-17 | Merchant Login and Logout | Merchant can login to the profile page with valid credentials | Merchant
18 | 18 | CapStore Pdf | Must | US-18 | Managing Cart | Customer can add and remove product | Customer
19 | 19 | CapStore Pdf | Must | US-19 | Sorting Product | Sorting product based on best seller, most viewed, product price in ascending and descending order and in given range of price | Customer
20 | 20 | CapStore Pdf | Must | US-20 | Search | Customer can search based on products and brands. | Customer
21 | 21 | CapStore Pdf | Must | US-21 | Getting Shipping Details | Placing an order will take all the shiping details of customer. | Customer
22 | 22 | CapStore Pdf | Must | US-22 | Transaction Process | Getting transactional details from user's account and updating. | Customer
23 | 23 | CapStore Pdf | Must | US-23 | Placing Order | Show details of order after placing | Customer
24 | 24
25 | 25
26 | 26
27 | 27
28 | 28
29 | 29
30 | 30
31 | 31
32 | 32
33 | 33
34 | 34
35 | 35
36 | 36
37 | 37
38 | 38
39 | 39
40 | 40
41 | 41
42 | 42
43 | 43
44 | 44
45 | 45
46 | 46
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.