## Sprint Backlog(Scrum - Cust (2)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | US-18 | 1 | Customer can add and remove product | Paras | 2019-05-10 | 10 hrs | 3 hrs |  | 13 hrs
2 | US-19 | 1 | Sorting Product | Arpita | 2019-05-10 | 8 hrs | 4 hrs |  | 12 hrs
3 | US-20 | 1 | Search | Himanshu | 2019-05-10 | 6 hrs | 1 hrs |  | 7 hrs
4 | US-21 | 1 | Getting Shipping Details | Shubham | 2019-05-10 | 6 hrs | 0 |  | 6 hrs
5 | US-22 | 1 | Transaction Process | Ravi | 2019-05-10 | 5 hrs | 0 |  | 5 hrs
| US-23 | 2 | Placing Order |  |  | 5 hrs | 1 hr |  | 6 hrs
6 | US-18 | 1 | Managing Cart UI | Vinoth | 2019-05-10 | 9 hrs | 0 |  | 9 hrs
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Title Page
RD.045 MoSCoW List |  | <Document Reference Number>
2019-10-10 10:39
OUM
RD.045 MoSCoW List
<Company Long Name>
<Subject>
| Author: | <Author>
| Creation Date: | 2010-01-01
| Last Updated: | 2010-01-01
| Document Ref: | <Document Reference Number>
| Version: | 0.1
Approvals
| Approver | Signature
<Approver 1>
<Approver 2>

## General Instructions
RD.045 MoSCoW List |  |  |  |  | <Document Reference Number>
2019-10-10 10:39
General Instructions
1 | Use this template to create a MoSCoW (Must have, Should Have, Could Have, or Won't Have) Requirements Work Product.
2 | Also consider using this template as a traceability matrix. Additional Sheets have been provided after the MoSCoW sheet that will facilitate the traceability of high level requirements to functional requirements, to business rules, to Service Oriented Architecture, to Test Cases, as appropriate for individual projects.
3 | This work product is meant to scale up or down; under some conditions, you may want to merge work products from other tasks into this one as additional sheets. In some situations, the project may be very large, in that case, it is recommended that an automated tool is used such as Oracle Enterprise Repository, rather than using this spreadsheet to produce your work product.
4 | Each individual worksheet contains instructions on how it should be used. See cells with comments as indicated by the red triangle in the upper right corner of the cell.
|  | Condition | Approach
|  | COTS Functionality | For Commercial Off the Shelf Software requirements stated in the Statement of Work or in the Project Charter, add a line to the Original Requirements sheet and to the MoSCoW list. If you are using the MoSCoW as a traceability matrix, you will need to tie the test case that authenticates the requirement to the requirement on the MoSCoW list.
|  | Requirements on MoSCoW tab without Use Case ID's | Requirements should tie to another form of implementation that satisfies the requirement. Some examples are COTS, Business Rules, Service, Non-functional Requirement.
|  | Use Case Catalog | When there are more than 20 use cases consider breaking up this catalog into multiple sheets by package groups (i.e. Data Access, Architecture, Data Acquisition), or by Actor (Procurement Manager, Buyer, Accounts Payable Specialist).
|  | New requirements may be added to the Original Requirements sheet | When Requirements are added to the Original Requirements sheet they should have a Source other than the Statement of Work(i.e. Meeting Minutes, CR, etc. with the corresponding dates).
|  | Business Rules or calculations may be managed within the application, or enterprise repository | Review the task RA.027 Identify Candidate Business Rules to understand how rules may be identified from use cases. Consider entering candidate Business Rules specified in the SOW or in subsequent work sessions into the RA.027, but manage rules/calculations within the application or tool. You may choose to combine the spreadsheet from the RA.027 into this workbook for smaller projects.
|  | SOA Services may be managed within a middleware tool or within the enterprise repository | You should review the task RA.025 Identify Candidate Services. You may choose to combine the spreadsheet from the RA.025 into this workbook for smaller projects.
|  | Scrum Product backlog and Sprint Backlog are included in this workbook | Project Managers using a Scrum approach to project management will use the last two sheets of this workbook for the Product Backlog and Sprint Backlog. Please review the Using Scrum in OUM White paper prior to using these sheets.

## Sheet Definitions
Worksheet | Purpose
Original Requirements | This worksheet identifies the original requirements gathered from the contract, the statement of work (SOW), and the Proof of Concept (POC) and any other relevant collateral provided from project definition.
RD.045.Moscow List | This worksheet categorizes and prioritizes the requirements. At a minimum, this sheet should hold requirements as defined in the statement of work or project charter. At the start of the project, the requirements listed in the "Original Requirements" and the "RD.045 MoSCoW List" tab would normally be the same, or at least, there should be a 100% coverage between the two.
RA.023 Use Case Catalog | List all the Use Cases for the project from the RA.023 Use Case Model, and cross reference back to the MoSCoW sheet for the requirement that the use case satisfies.
RD.055 Supplementary Req | Use this sheet to record the Supplemental Requirements for the project. See the task guideline for the Task RD.055 Detail Supplemental Requirements
RA.025 Services Traceability | Use this sheet to capture traceability back to the Services that are documented in the work product for Task RA.025 Identify Candidate Services.
RA.027 Rules Traceability | Use this sheet to capture traceability to Business rules that are documented in the work product for Task RA.027 Identify Candidate Business Rules. For small projects you may choose to combine work products and insert the RA.027 work product here.
TE.0xx Test Traceability | This worksheet tracks test cases as outlined in the Test Plan. This worksheet can be used to populate the Test results work product(s) if a formal document is required.
RD.042 Glossary Traceability | Project Glossary used for traceability across multiple work products. Common terms used in this spreadsheet should be documented here to ensure terms used in the requirements are understood by both technical and business project members. If the term changes, impact analysis can be done to determine which artifacts would require the term change.

## Document Control
RD.045 MoSCoW List |  |  |  |  | <Document Reference Number>
2019-10-10 10:39
Document Control
Change Record
| Date | Author | Version | Change Reference
| 2010-01-01 | <Author> | 0.1
Reviewers
| No | Name | Position | Note

## Original Requirements
MoSCoW ID | Source | Priority (M/S/C/W) | Original Requirement Summary | Stakeholder | Comments | Acceptance Criteria | Test Scenarios
1 | SOW | M
2 | Business Req Workshop | C
3 | RFP | S
5 | mm-dd-yy Req Workshop minutes | W
6 | BA.040 Customer Diagnostic Information
7
8
9
10
11
12
This worksheet is intended to document the requirements specified in the original RFP, Statement of work, or Contract in a tabular format, which is reviewed and agreed upon by the project management and the project sponsors. The Project Management plan (PMP) should reference this worksheet. This worksheet enables traceability back to the original SOW, as requirements become further quantified/qualified.
Note - Assumptions defined in RFP, SOW and/or associated documentation are documented as original requirements in this worksheet with ownership appropriately defined. Early in the project, these requirements may not yet be prioritized by increment, but are used to provide traceability to other work products that address them. When Requirements are added to the Original Requirements sheet they should have a Source other than the Statement of Work (i.e. Meeting Minutes, CR, etc. with the corresponding dates).

## RD.045 MoSCoW List
MoSCoW ID | Source | Priority (M/S/C/W) | GAP (COTS/Custom) | Requirement Description | Owner | Complexity | Risk/ Impact | Use Case ID | Work Product Cross Reference/Details sheet | Business Process | Business Goal | Objectives | Scope | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Comments | Acceptance Criteria | User Acceptance Test Case ID
1 | [7 empty] | UC:nnn
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
Use this sheet to document confirmed priorities and map requirements to use cases and COTS functionality. Optionally, cells may color-coded to indicate the system which will support/perform the high level requirement

## RA.023 Use Case Catalog
MoSCoW ID | Use Case ID | Use Case Name (verb/noun) | Actors | Iteration Group | Customer Priority | Risk/ Impact | Complexity | Use Case Dependency | Source | Date | Package | Comment | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
UC.nnn
This worksheet is intended to be used to capture a catalog of the Use Cases, this list is taken from the RA.023 Use Case Model.

## RD.055 Supplemental Req
MoSCoW ID | Supplemental ID | Source | Date | Supplemental Type | Supplemental Requirement Name | Requirement Description | Risk/ Impact | Comment | Acceptance Criteria | Test Scenario ID(s)
SUP.001
This worksheet is used to capture details associated to supplemental requirements such as; supplementary, non-functional and Quality of Service requirements are not commonly captured by use cases and generally revolve around usability, reliability, operability, safety, compatibility and transferability, performance and supportability, legal and regulatory requirements, application standards, support, interface requirements etc.
These requirements are further detailed;
Audit, globalization and localization, legal requirements are documented in task RD.070 Determine Audit and Control Requirements
User Interface Standards requirements are documented using task IM.005 Develop Conceptual Prototype
Architectural Requirements are documented in task TA.020 Define Architecture Requirements and Strategy
Documentation Requirements are documented in task DO.010 Define Documentation Requirements and Strategy
Performance Requirements are documented in task PT.020 Define Performance Management Requirements and Strategy

## RA.025 Services Traceability
This sheet for "candidate" SOA services (RA.025) may be used to trace SOA Services to associated Use Cases
** This worksheet can be used to trace SOA Services to use cases. The purpose of this traceability is to ensure that if a Service changes, all effected use cases can identified and subsequently tested.
Services may later be implemented in different ways (1:1 relationship to a white box Use Case or a single step on the System side of a black box user goal use case)
If the service maps to only a single step of a UC, please enter the step number of the Use Case step that refers to the service during Design (DS.120)
Services should be documented using the SERVICES PORTFOLIO either using the Enterprise repository tool or using the work product associated with the Identify Candidate Services (RA.025) task.
Use Case names and numbers are manually maintained on this sheet. It is important to note that these will need to be changed anytime the UC Names or Numbers on the RA.023 or RA.024 work products are adjusted.
|  |  |  | UC: Name 10.00 | UC: Name 15.00 | UC: Name 20.00 | UC: Name 30.00 | UC: Name 40.00 | UC: Name 50.00 | UC: Name 60.00 | UC: Name 70.00
MoSCoW ID | Service ID | Service Name | Contract ID | UC.10.00 | UC 15.00 | UC 20.00 | UC 30.00 | UC 40.00 | UC 50.00 | UC 60.00 | UC 70.00
| SV.001 |  |  | X |  |  |  |  | X
| SV.002 |  |  | Step xx
STEP xx = One step of use case is realized by this Service (*note this is manually maintained if the UC steps need to be renumbered)
X in UC column = Use case is realized Entirely by this Service

## RA.027 Rules Tracability
This sheet for "candidate" Rules (RA.027) may be used to trace Rules to associated Use Cases
** This worksheet can be used to trace Rules to use cases. The purpose of this traceability is to ensure that if a Rule changes, all effected use cases can identified and subsequently tested.
Project Rules are Identified from a number of sources including the original textual requirements, Enterprise Rules Repository, if available as well as
Use Case and Business Process development
Rules should be documented using a Rules Repository either using a Rules Engine directly into a software product, the Enterprise repository tool or using the work product associated with the Identify Candidate Rules (RA.027) task.
|  |  | UC: Name 10.00 | UC: Name 15.00 | UC: Name 20.00 | UC: Name 30.00 | UC: Name 40.00 | UC: Name 50.00 | UC: Name 60.00 | UC: Name 70.00
MoSCoW ID | Business Rule ID | Name | UC.10.00 | UC 15.00 | UC 20.00 | UC 30.00 | UC 40.00 | UC 50.00 | UC 60.00 | UC 70.00
| BR.001 |  |  | X |  |  |  | X |  |  | X
BR.002
BR.003
BR.004
BR.005
BR.006
BR.007
BR.008
BR.009
BR.010
BR.011
BR.012
BR.013
BR.014
BR.015
BR.016
BR.017
BR.018
BR.019
BR.020
BR.021
BR.022
BR.023
BR.024
BR.025
BR.026
BR.027
BR.028
BR.029
BR.030
BR.031
BR.032
BR.033
BR.034
BR.035
BR.036

## TE.0xx Test Tracability
This worksheet is intended to be used to document test scenarios and test results based on the Test Plans.
This sheet could be duplicated once for each type of test if the number of tests in the sheet becomes too large
MoSCoW ID | Test Scenario ID | Test Type | Test Scenario Name | Result (Pass or Fail) | Tester | Comments
| U001 | Unit
| INT010 | Integration
| SYS101 | System
| SYSINT010 | Systems Integration
| UAT010 | Acceptance
Test results may be recorded and traced back to requirements on the MoSCoW as a result of the following:
TE.030 Unit Test
TE.040 Integration Test Results
TE.070 System Test Results
TE.100 Systems Integration Test Results
TE.120 Acceptance Test Results

## RD.042 Glossary Xref
Term | Artifact Name | Artifact Name | Artifact Name | Artifact Name | Artifact Name
This worksheet is for project reference, and is not intended to replace the Glossary (RA.042) in OUM. The worksheet is a cross reference which identifies project artifacts where a term has been directly referenced. This helps with impact analysis in order to determine, which work products may need to be updated if changes to the term are made.

## Sprint Backlog (Scrum)-Cust 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | US.1 | 1 | Customer is logged in |  | 2019-05-10
|  | 2 | Customer can access profile page | Indu
2 | US.2 | 1 | Merchant/admin upload the image |  | 2019-05-10
|  | 2 | Customer can view the product image | Mohit
3 | US 3 | 1 | CapStore Homepage | Akash | 2019-05-10
4 | US 4 | 1 | Product List Page |  | 2019-05-10
|  | 2 | Product Page | Ankita
5 | US 5 | 1 | Customer Profile |  | 2019-05-10
|  | 2 | My Orders
|  | 3 | Return Goods | Ajay
6 | US 6 | 1 | Order Placed |  | 2019-05-10
|  | 2 | Generate Invoice | Tannya
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Sprint Backlog(Scrum -Merchant)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
12 | US.1 | 1 | Merchant profile Page | Pavizha | 2019-05-10
|  | 2 | Designing Merchant profile page | Pavizha | 2019-05-10
13 | US-3 | 1 | Managing inventory | Nishanthini | 2019-05-10
|  | 2 | Adding items to the Inventory | Nishanthini | 2019-05-10
|  | 3 | Removing products from inventory | Nishanthini | 2019-05-10
14 | US-4 | 1 | Search products | Diksha | 2019-05-10
|  | 2 | Search Orders | Diksha | 2019-05-10
15 | US-5 | 1 | Image Upload of products | Nitin Beri | 2019-05-10
16 | US-6 | 1 | Delivery products | Vignesh | 2019-05-10
|  | 2 | Updating Inventory | vignesh | 2019-05-10
17 | US-2 | 1 | Merchant Login | Nitin Beri | 2019-05-10

## Sprint Backlog(Scrum - Cust2 )
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | US-18 | 1 | Customer can add and remove product | Paras | 2019-05-10 | 10 hrs | 3 hrs |  | 13 hrs
2 | US-19 | 1 | Sorting Product | Arpita | 2019-05-10 | 8 hrs | 4 hrs |  | 12 hrs
3 | US-20 | 1 | Search | Himanshu | 2019-05-10 | 6 hrs | 1 hrs |  | 7 hrs
4 | US-21 | 1 | Getting Shipping Details | Shubham | 2019-05-10 | 6 hrs | 0 |  | 6 hrs
5 | US-22 | 1 | Transaction Process | Ravi | 2019-05-10 | 5 hrs | 0 |  | 5 hrs
| US-23 | 2 | Placing Order |  |  | 5 hrs | 1 hr |  | 6 hrs
6 | US-18 | 1 | Managing Cart UI | Vinoth | 2019-05-10 | 9 hrs | 0 |  | 9 hrs
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Sprint Backlog(Scrum-Admin)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | US-7 | 1 | sign up page for merchant | Nitin | 2019-05-10 | 10 hrs | 3 hrs |  | 13 hrs
|  | 2 | sign up page for customer
2 | US-8 | 1 | Display all details of customer | Sanjivani | 2019-05-10 | 8 hrs | 4 hrs |  | 12 hrs
|  | 2 | Display details of Inventory
|  | 3 | Display all details of merchant
3 | US-9 | 1 | Admin can generate buiseness anlyasis | Bittu | 2019-05-10 | 6 hrs | 1 hrs |  | 7 hrs
4 | US-10 | 1 | Admin can add or remove a merchant | Pavithra | 2019-05-10 | 6 hrs | 0 |  | 6 hrs
5 | US-11 | 1 | Checking status of delivery | Priya | 2019-05-10 | 5 hrs | 0 |  | 5 hrs
|  | 2 | updating status of delivery |  |  | 5 hrs | 1 hr |  | 6 hrs
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.